## Summary Cover
Project: | [6 empty] | CONTRACT NO. |  |  | PAGE 1
"2018 Pavement Rehabilitation contract"Town Of Hull" NANTASKET AVE. FROM Q ST. TO Y ST. | [6 empty] | APPLICATION FOR PAYMENT NO.: |  |  | TWO
PAYMENT PERIOD
[7 empty] | FROM: | 2019-09-11 | TO: | 2019-09-27
OWNER:Town Of Hull |  |  |  | CONTRACTOR:T.L.Edwards,Inc. |  |  |  | ENGINEER:
253 Alantic Avenue,Hull,Ma. 02046 ATT:Mr. Phillip Lemnios |  |  |  | 100 Wales Ave.(rear) Avon,Ma. 02322 |  |  |  | BETA Group, Inc. 315 Norwood Park South Norwood,Ma. 02062
Contract Date: | October 17th,2018 |  | Estimated Completion Date: | [5 empty] | Percent Complete: |  | 32.06%
CONTRACT CHANGE ORDER SUMMARY |  |  |  |  | APPLICATION FOR PAYMENT SUMMARY
No. | Approval Date | Additions | Deductions |  | 1. Original Contract Amount ……...……………………. |  |  |  |  | 436489.5
ONE | ADD/Mobilzation | 25000 |  |  | 2. Total Change Orders to Date*…………..….………… |  |  |  |  | 114144
TWO | ADD/Drainage | 89144 |  |  | 3. Current Contract Amount (1+2) ……………………… |  |  |  |  | 550633.5
[5 empty] | 4. Total Value of Work Completed to Date*…..…...…… |  |  |  |  | 176528.45
[5 empty] | 5. Total Retainage to Date (5%)* ………………………. |  |  |  |  | 8826.45
[5 empty] | 6. Total Amount Payable to Date ………….…………… |  |  |  |  | 167702
[5 empty] | 7. Less Previous Payments……………...…………….. |  |  |  |  | 17925.17
Total Change Orders: |  | 114144 | 0 |  | 8. AMOUNT DUE THIS APPLICATION (6-7) ……….……... |  |  |  |  | 149776.83
Net Change: |  | 114144 | 0
* Detailed breakdown attached
CONTRACTOR'S CERTIFICATION: | [6 empty] | ENGINEER'S CERTIFICATION:
The undersigned Contractor certifies that to the best of the Contractor's knowledge, information and belief: (1) all prior progress payments received from Owner on account of Work completed under the Contract have been applied on account to discharge Contractor's legitimate obligations incurred in connection with Work covered by prior Applications for Payment; (2) title of all Work, materials and equipment incorporated in said Work or otherwise listed in or covered by this Application for Payment will pass to the Owner at time of payment free and clear of all Liens, security interests and encumbrances (except such that are covered by a Bond acceptable to the Owner indemnifying Owner against any such Liens, security interests and encumbrances); (3) all Work covered by this Application for Payment has been completed in accordance with the Contract Documents and is not defective; and (4) the amount indicated under this Application for Payment is now payable and due. | [6 empty] | The undersigned certifies on behalf of the Engineer that the Work has been inspected and to the best of their knowledge, understanding and belief, the quantities shown and the dollar amount due under this Application for Payment are correct and all Work completed by the Contractor has been performed in accordance with the Contract Documents.
Engineer : BETA Group, Inc.
Date: ________
Contractor: | [6 empty] | Approved By:
By: ______________________________ Date: _______________ | [6 empty] | By: ____________________________ Date: _______________
Name: | [6 empty] | Name:
Title: | [6 empty] | Title:
Approved For Payment:
By: ______________________________ Date: _______________ | [6 empty] | By: ______________________________ Date: _______________
Name: | [6 empty] | Name:
Title: | [6 empty] | Title:
By: ______________________________ Date: _______________ | [6 empty] | By: ______________________________ Date: _______________
Name: | [6 empty] | Name:
Title: | [6 empty] | Title:
Date: ________
DISTRIBUTION TO:
OWNER: _________ CONTRACTOR: _________ ENGINEER: _________ MWRA: _________ OTHERS: _______________________

## Item by Item Breakdown
[5 empty] | APPLICATION FOR PAYMENT NO. |  | ONE (1)
OWNER: |  |  |  |  | PERIOD 00/00/09 THRU 00/00/09 |  |  |  | ENGINEER:
[5 empty] | PAGE 2 OF 6 |  |  |  | BETA GROUP, INC.
CONTRACTOR:
ITEM NO. | SCOPE OF WORK/DESCRIPTION | EST. QUANTITY | UNITS | UNIT BID PRICE | CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL THIS PAGE | 0 |  | 0 |  | 0 |  | 0
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
[5 empty] | APPLICATION FOR PAYMENT NO. |  | ONE (1)
OWNER: |  |  |  |  | PERIOD 00/00/09 THRU 00/00/09 |  |  |  | ENGINEER:
[5 empty] | PAGE 3 OF 6 |  |  |  | BETA GROUP, INC.
CONTRACTOR:
ITEM NO. | SCOPE OF WORK/DESCRIPTION | EST. QUANTITY | UNITS | UNIT BID PRICE | CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | TOTAL THIS PAGE | 0 |  | 0 |  | 0 |  | 0
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
[5 empty] | APPLICATION FOR PAYMENT NO. |  | ONE (1)
OWNER: |  |  |  |  | PERIOD 00/00/09 THRU 00/00/09 |  |  |  | ENGINEER:
[5 empty] | PAGE 4 OF 6 |  |  |  | BETA GROUP, INC.
CONTRACTOR:
ITEM NO. | SCOPE OF WORK/DESCRIPTION | EST. QUANTITY | UNITS | UNIT BID PRICE | CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL THIS PAGE | 0 |  | 0 |  | 0 |  | 0
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
[5 empty] | APPLICATION FOR PAYMENT NO. |  | ONE (1)
OWNER: |  |  |  |  | PERIOD 00/00/09 THRU 00/00/09 |  |  |  | ENGINEER:
[5 empty] | PAGE 5 OF 6 |  |  |  | BETA GROUP, INC.
CONTRACTOR:
ITEM NO. | SCOPE OF WORK/DESCRIPTION | EST. QUANTITY | UNITS | UNIT BID PRICE | CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK
|  |  |  | AMOUNT CARRIED FORWARD | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | TOTAL THIS PAGE | 0 |  | 0 |  | 0 |  | 0
|  |  |  | CONTRACT SUBTOTAL | 0 |  | 0 |  | 0 |  | 0
[5 empty] | APPLICATION FOR PAYMENT NO. |  | ONE (1)
OWNER: |  |  |  |  | PERIOD 00/00/09 THRU 00/00/09 |  |  |  | ENGINEER:
[5 empty] | PAGE 6 OF 6 |  |  |  | BETA GROUP, INC.
CONTRACTOR:
CHANGE ORDER SUMMARY
C.O. NO. | CHANGE ORDER REFERENCE / DATE SCOPE OF WORK/DESCRIPTION |  |  |  | CHANGE ORDER CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK | % OR QUANTITY | VALUE OF WORK
| (NONE TO DATE) |  |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  |  |  | CHANGE ORDER SUBTOTAL | 0 |  | 0 |  | 0 |  | 0
APPLICATION FOR PAYMENT SUMMARY
SCOPE OF WORK/DESCRIPTION |  |  |  |  | CONTRACT AMOUNT | PREVIOUS APPLICATION FOR PAYMENT |  | WORK DONE THIS PERIOD |  | TOTAL TO DATE
[6 empty] | % COMPLETE | VALUE | % COMPLETE | VALUE | % COMPLETE | VALUE
[7 empty] | OF WORK |  | OF WORK |  | OF WORK
| TOTAL OF PAYMENT ITEM 1 THRU ____________ |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0
| TOTAL CHANGE ORDERS |  |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
| TOTAL VALUE OF WORK TO DATE |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0
[10 empty] | TOTAL VALUE OF WORK TO DATE | 0
[10 empty] | TOTAL RETAINAGE TO DATE | 0
[10 empty] | AMOUNT PAYABLE TO DATE | 0
[10 empty] | LESS PREVIOUS PAYMENTS | 0
[7 empty] | TOTAL AMOUNT PAYABLE THIS APPLICATION |  |  |  | 0